## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-10-07 | Edric Antoine | P4 | Resolved | Edric Antoine | When touching a wall from the bottom or top, can only move left or right sometimes. | When touching a wall from the bottom or top, the player should be able to move left and right freely. | When touching a wall from the bottom or top, the player is only able to move left if they are on the leftmost part of the wall, and right on the rightmost part of the wall. | Touch a wall from the bottom or top, and attempt to move left and right while doing so.
2 | 2024-10-11 | Carina Bi | P3 | Resolved | Clement To | Once bullets leave the screen, they eventually wrap back around again instead of disappearing | Once bullets fly off the screen, they should not show up on the screen again. They should disappear indefinitely | When bullets fly off the screen, they do not disappear and reappear from the other side. | Shoot bullets, wait for maybe 10 seconds and they should appear again
3 | 2024-10-12 | Edric Antoine | P3 | Resolved | Edric Antoine | Rapidly firing bullets will cause them to collide with each other and disappear. | All 6 bullets fired before having to reload should be on screen until they naturally despawn. | Out of the 6 bullets fired before having to reload, up to 3 or 4 of them can disappear. | Shoot bullets as fast as possible and count how many are on screen before having to reload. The expected number should be 6.
4 | 2024-10-12 | Andy Choi | P3 | Resolved | Edric Antoine | When running in the same direction as the bullets fired, the player can get collide with their own bullets and the bullet disappears | The bullet fired by the player shouldn't be affected by the players collision | The bullet fired by the player disappears if the player collides with it | Run infront of the bullets being fired
5 | 2024-10-12 | Mike Wang | P3 | Resolved | Carina Bi | Bullets are fired at a slight upward angle from the mouse cursor. | The bullets should travel in the direction of the mouse cursor | Bullets appear to fire slightly off from the cursor's location. It also seems to get worse as the cursor moves towards the player. | Try shooting some bullets to the left/right. The bug is less pronounced towards the top/bottom of the screen.
6 | 2024-10-23 | Mike Wang | P3 | Resolved | Andy Choi | The game may occasionally crash when trying to load the main level | After loading the new level and playing around, the game should not crash | The game crashes with the following error:outlaws_ascent: /home/mike/Documents/CPSC427/Team14/src/tiny_ecs.hpp:81: Component &ComponentContainer<KnockbackTimer>::get(Entity) [Component = KnockbackTimer]: Assertion `has(e) && "Entity not contained in ECS registry"' failed. Aborted (core dumped) | Try loading the new level by pressing "L". Then try moving around and shooting enemies.
7 | 2024-10-30 | Mike Wang | P2 | Resolved | Edric Antoine | The player can occasionally get stuck in a cactus. | The player should get knocked back when touching a cactus | The player glitches and gets stuck. Pressing movement keys/shift dash do not work. This bug is also more prevalent on Mac and Linux | (NOTE: difficult to reproduce consistently) Try moving into the cactus from multiple angles. Try to use knockback from an enemy's bullets to collide with the cactus
8 | 2024-10-30 | Mike Wang | P3 | Resolved | Mike Wang | When the player dashes into an enemy, no collision occurs | A collision should be reported when the player touches an enemy while dashing, and knockback/damage should be applied | The player "clips" through the enemy while dashing, as if no collision occurred | Try to dash into the enemy
9 | 2024-10-30 | Mike Wang | P4 | Resolved | Mike Wang | Enemies do not collide with each other | When an enemy touches another enemy, a collision should be registered. However, no knockback/damage should be applied. | Enemies "clip" through each other, as if no collision occurred | Load the main level with "L". Go to the "boss" room in the lower right corner, and wait. The enemies will try to walk towards you
10 | 2024-10-30 | Mike Wang | P5 | Resolved | Mike Wang | Enemies tend to pathfind towards the exact same location relative to the player | There should be some variation in the position that enemies pathfind towards you | Each enemy, regardless of their initial position, tends to walk towards the same final position | Load the main level with "L". Go to the "boss" room in the lower right corner, and wait. The enemies will try to walk towards you
11 | 2024-10-31 | Clement To | P4 | Resolved | Mike Wang | Unequipped weapons from swapping are considered as a collidable entity and they can block bullets | Unequipped weapons are not rendered and is not considered as an entity that can interact with others, do not block bullets | when the player swaps their weapon, the previous weapon stays in the last position and can collide with bullets, thus bullets disappear from the screen | have more than 1 weapon equipped, then swap to another weapon without moving, the weapon will now collide with the player and bullets fired may disappear because they collide with the invisible weapon
12 | 2024-10-31 | Mike Wang | P5 | Resolved | Mike Wang | The player's arms get temporarily dislocated when running or dashing into obstacles | The player's arms and weapon should remain stationary relative to the player at all times | When a player runs or dashes into an obstacle, the arms and weapon get temporarily shifted from their original position. Moving away causes them to go back | Try running or dashing into any obstacle that doesn't knock you back
13 | 2024-11-01 | Mike Wang | P4 | Resolved | Andy Choi | When the enemy/player is hit by multiple shotgun bullets, the hurt sound plays multiple times | The hurt sound should only play once | The hurt sound plays for each projectile that collides, which causes an interesting sound effect | Pick up a shotgun, and move close to the enemy so that most bullets hit the enemy.
14 | 2024-11-04 | Mike Wang | P4 | Resolved | Andy Choi/Mike Wang | There are some artifacts around the edge of the screen when the lowhealth shader is applied | The distortion should be minimized towards the edges to avoid artifacts/clipping (try the smoothstep function in the fragment shader) | The textures tend to clip/artifact towards the edges of the screen. It is more visible when the player is near a fence wall | Walk near a fence wall. Get damaged enough to trigger the lowhealth distortion shader.
15 | 2024-11-11 | Carina Bi | P3 | Resolved | Edric Antoine | When an item is picked up right before inventory tab is open, item description is layed over inventory ui | Item description should not be rendered over inventory ui | Item description is rendered over inventory UI and blocks inventory items | Pick up a passive item, immediately press tab
16 | 2024-11-14 | Mike Wang | P4 | Resolved | Carina Bi | When the player heals to get out of "low hp", the lowhealth shader is not disabled | The lowhealth shader should not be rendered whenever the player is healthy | When healing from low hp back up, the lowhealth shader effect persists | Try getting to low hp (around 40%), then pick up and use the "hearty stew" item that heals to full hp.
17 | 2024-11-16 | Andy Choi | P4 | Resolved |  | When the player plays a landmine and attempts to use the same empty item slot, the game crashes | The game should not crash | The player should be able to press the empty item slot without issue | If the land mine is in slot 1 I press 1 and it places the landmine, if I try pressing 1 again it'll crash
18 | 2024-12-01 | Carina Bi | P2 | Resolved |  | Reloading to level from different level puts you in wrong level | Should reload to level from save (level should be persisted) | Reloading into NEXT level: ie if save in tutorial, then clicking reload in desert, you will end up in the forest | Save the game when you are in the tutorial. Toggle L to move to desert level. Press F4 to try to reload the game. You will end up in the forest
19 | 2024-12-01 | Carina Bi | P3 | Resolved |  | Missing limbs if you press L when in inventory screen | Should just move to the other level, limbs intact | limbs are missing | Press esc to go to the inventory screen, while still in inventory screen, press L

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release